## Meeting Folllow Up
Yemen Shelter/NFI/CCCM Meeting Action Points and Folllow Up Matrix
No. | Action Point description | Responsible | Due Date | Update | Status
General Cluster Meeting of 14th May 2017
1 | CCT to share translated AAP documents and signed beneficiary information sharing framework. The endorsed MoM is to be published on the web portal | Monir | ASAP | AAP document translated and shared with Cluster. Minutes translated into Arabic and shared on the Cluster web portal | Completed
2 | CCT is to share Hudaydah mission report as well as an updated contingency stock list. | Monir | ASAP | Hudaydah mission report shared on the Cluster web portal. Updated contingency stock list shared | Completed/Ongoing
3 | CCT to review and provide technical feedback on submitted projects as well as keeping members up to date of status of YHPF allocations. | Charles | ASAP | Review process completed 5/7 projects recommended by OCHA and being reviewed by OCHA New York. 10 projects completed one of which is for Shelter. Update of YHPF provided during the meeting. Other 4 Shelter projects to be signed in the next few weeks | Completed
4 | CCT to coordinate with all actors in order to be able to finalize the PMR. | Charles | ASAP | PMR draft shared with SAG/TWIG for comments but none received final draft sent to OCHA for finalisation. Final PMR 2017 will be shared to all once completed | Completed
SAG/TWIG meeting of 29th May 2017
1 | IOM implementing partner (Basma) will share the list of 600 HHs assisted with NFIs in Hajjah. | Hani | ASAP | List of 600 targeted families was shared by IOM and UNHCR agreed to cover the remaining 400 through Abs Foundation who just completed the beneficiary identification process with 397 families identified. Around 117 additional families were aslo identified and would be shared with UNHCR. | Completed
2 | Cluster Co-Chair to summarize Emergency Response guideline learning from experience of the recent emergency in Hajjah. | Hani | 2017-07-06 | Two drafts completed, final draft to be completed by next meeting | Ongoing
3 | CCT will share the IST and the finalized cluster simplified needs assessment forms. | Charles/Monir | 2017-07-16 | Proposal of including Cluster needs assessment format in IST to be discussed at next ICCCM meeting. CCT did not attend the last one. If proposal is accepted and agreement is reached form to be finalised and shared. Charles to raise issue at next ICCCM. | Ongoing
4 | CCT will communicate with OCHA on the IST Assessment timeframe, agree on response time and clarify when Cluster may decide to go ahead with needs assessment. | Monir | ASAP | Meeting was held with Stephanie and agreement to the principle was obtained. She confirmed no overlap between TFPM, RRM and IST. If IST was not run within 72 hrs then Cluster can initiate their own assessment. Proposla to include cluster assessment in IST should be raised at the next ICCM meeting. | Completed
5 | CCT to support on the negotiation of easing the process of coordination with the authorities. | Hani | ? | Access WG has a mechanism to track access issues and attempt to resolve issues. CCT is suggesting to extend support to the access working group to enhance the system. However the gaps in the mechanism need to be identified so we can see where we can bring an added value. | Ongoing
6 | Suggestion to institute a system of tracking issues encountered by Partners to negotiate with the authorities however should be clarified with OCHA process to not create another layer of coordination/reporting without added value. | Hani | ASAP |  | Ongoing
7 | Since the Access Working Group also dealt with difficulties in access to certain locations they should be liaised with before any action is taken | Hani | ASAP |  | Ongoing
8 | Cluster Coordination Team to send the recently finalized Rental Subsidy Guidelines to partners. | Monir | 2017-06-18 | Guidelines were shared with minutes on 31/05/2017 | Completed
9 | Call for Expression of Interest for Ibb Governorate sent out on 14/06/2017 | Charles/Monir | 2017-06-14 | CEI was sent out on 14/06/2017 with deadline on 04/07/2017 after which a decision would be made on who would be the Sub National Cluster coordinator for Ibb Governorate | Ongoing
General Cluster Meeting of 18th June 2017
1 | Cluster Coordination Team (CCT) will update the cluster structure map to include contact information of the sub-national cluster coordinators. | Monir
2 | CCT will share the IST and the finalized cluster simplified needs assessment forms | Monir
3 | Cluster Co-Chair is currently summarizing the Emergency Response guideline learning from experience of the recent emergency in Hajjah. | Hani
4 | Further follow up required with OCHA to understand the limitation of the existing system of tracking access issues and contribute to improve the system | Hani
5 | CCT to request OCHA to give a presentation to Cluster the FTS (Financial Tracking System) | Charles | 2017-06-29
6 | CCT will share the draft version of the UNHCR EESK with the cluster partners | Monir
7 | It was agreed to prioritize the development of tools for operationalizing the rental subsidies guideline | Hani
8 | CCT will share a draft of cash for shelter tools | Hani
9 | Expression of interest sent by HI for the provision of inclusion technical support will be circulated by the CCT to all partners. | Monir
10 | CCT will circulate the registration form of the training. | Monir
11 | CCT will circulate the survey maximum by tomorrow | Monir
12 | CCT to follow up with the access working group on the access tracking to identify gaps that we can support to improve the process. | Hani

## Mission Follow up
Yemen Shelter/NFI/CCCM Mission Action Points and Folllow Up Matrix
No. | Action Point description | Responsible | Due Date | Update | Status
Mission to Ibb 19-22nd June 2017
1 | To meet with ACTED end of July and assess whether CASH for rent is a suitable solution. | Charles/Monir | 2017-08-14
2 | In case CASH for rent works out, CCT will facilitate budget amendment with OCHA. | Charles | 2017-08-16
3 | CCT to advice on site management assessment form. | Charles | 2017-07-10 | Sent email to Jessica and she will share project details and forms after Eid | Ongoing
4 | The list of priority IDP Hosting sites will also be shared with ACTED | Monir | ASAP
5 | CCT to ensure IDP Hosting Sites assessed by ACTED are communicated to IOM to avoid overlaps and gaps. | Hani
6 | ACTED will consult with their country office and submit their candidature for Sub national Cluster Coordinator next week | Monir
7 | CCT to liaise with HFY while drafting CASH for rent tools. | Hani
8 | CCT will discuss at national level with OCHA on how to improve coordination in Ibb. | Charles | 2017-06-29
9 | CCT to support YRC in Ibb branch in linking up with potential Agencies and/or international NGOs. | Charles | 2017-07-06
Mission to Aden 6 - 13th July 2017
1
2
Mission