## Plan
Joint Sustainable Packaging Initiative Activity Plan
| Output/Activity | LEAD (TBC) | Participating Stakeholders (all TBC) | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | Indicators | NOTES
|  |  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Indicator | POLICY & ADVOCACY OUTPUT 1.1 Humanitarian assistance supply chain policy landscape is analysed and standardised and evidence-based advocacy is conducted by all JI partners. | bar: 2021 1 to 2025 4
# of NS development programmes, disaster response or recovery operations with community engagement and accountability approaches included | 1.1.1 Multi-donor policy landscape analysis for humanitarian assistance supply chain | JEU | USAID | [21 empty] | To understand the entire supply chain policy landscape, in order to better influence environmentally sustainable changes and integration as they are revised. Step 1 to inform 1.1.2. | bar: 2021 2 to 2021 3; 2022 1 to 2022 4; 2024 1 to 2024 4
| 1.1.2 Standardisation of policies and parameters governing humanitarian assistance supply chain actions | JEU | USAID, FCDO, IOM, UNHCR, SAVE, GLC | [21 empty] | This is about coordination between donors and humanitarian organizations. To the extent possible, make sure we all understand what is meant by certain requirements and try to ensure that these are harmonized. Led by the JEU in collaboration with other partners, and standardisation could be advocated for thru the Good Humanitarian Donorship Group if research proves it is needed. | bar: 2021 2 to 2022 4; 2024 1 to 2024 4
| 1.1.3 Sustainable packaging requirements - to include in guidelines, policies, regulatory requirements, funding applications, and project proposals | USAID / ECOS | ECHO, USAID, UNHCR, Save, GSC, ICRC, WFP | [21 empty] | 2021 - some initial research/outreach, linked to 1.1.3; 2022 - bulk of the activity. E.g. on including packaging waste management as part of their CSR. Advocacy should be coupled with 2-way dialogue with the private sector so that they're likewise informing policy-setting. | bar: 2021 3 to 2024 4
| 1.1.4 Guidance note on international & national policies governing plastic use | JEU | WFP, BRS, USAID, GSC ECOP, UNHRD, IOM | [21 empty] | Short guidance note “cheat sheet” for main HA contexts, including plastic bans, relevant Basel convention regulations, transboundary movements etc. Led by JEU with inputs from BRS and operational partners with experience of working with new regulations. | bar: 2021 3 to 2022 4; 2024 1 to 2024 4
| 1.1.5 Coordinated internal and external advocacy and communications | USAID / ECOS | All partners | [21 empty] | Ongoing throughout the JI, led by USAID/ECOS as part of the coordination function of the JI. Linked to communications output. | bar: 2021 1 to 2025 4
| 1.1.6 Private sector advocacy and policy setting | USAID / ECOS | WFP, GLC | bar: 2022 1 to 2022 4; 2024 1 to 2024 4
| 1.1.7 Packaging Sustainability (Grand) Challenge | USAID | GLC, WFP, JEU, IOM | [21 empty] | 2021 - 2022 begin innovation competitions (linked to activity 2.3.2) and 2023 - 2024 Grand Challenge. A Grand Challenge would be a multi-year process, but could start with smaller innovation competitions that could ultimately help inform a Grand Challenge (an umbrella for multiple types of innovation activities - challenges, prizes, etc) | bar: 2022 1 to 2024 4
Indicator | COMMUNICATIONS OUTPUT 1.2 The implementation of a communications strategy to 1) raise awareness of packaging sustainability issues and related good practices among key stakeholders & external audiences; and to 2) promote their engagement in the Initiative | bar: 2021 1 to 2025 4
| 1.2.1. Communications strategy | USAID / ECOS | All - Communications Working Group | [21 empty] | The strategy will include a set of measurable communications objectives (i.e. what are we aiming to achieve and how), agreed by the Initiative’s communications working group and partner representatives | bar: 2021 1; 2022 1 to 2022 4; 2024 1 to 2024 4
| 1.2.2 Communications working group | USAID/ECOS | All - Communications Working Group | [21 empty] | Set up in Q1 and meetings quarterly. Pooling communications expertise and resources from across the Initiative’s partner organizations to agree on strategy and establish the best activities and channels to promote sustainable packaging issues and promote engagement with the Initiative. | bar: 2021 1 to 2025 4
| 1.2.3 Planning calendar & 1.2.4 Key communications messages and other content | USAID / ECOS | All - Communications Working Group | [21 empty] | Set up in Q1. A tool to support planning of communications activities. It will record key milestones, events, and opportunities to share the Initiative’s messages. Messaging: Q1 2021 (set up); Updates as needed, and as other outputs are implemented. Messages will be aligned with and support the advocacy objectives (1.1) | bar: 2021 1; 2022 1 to 2022 4; 2024 1 to 2024 4
| 1.2.4 | USAID / ECOS | All - Communications Working Group | [21 empty] | Q1 2021 (set up); Updates as needed, and as other outputs are implemented. Messages will be aligned with and support the advocacy output objectives (1.1) | bar: 2021 1; 2022 1 to 2022 4; 2024 1 to 2024 4
| 1.2.5 Website used to disseminate advocacy messages | JEU + USAID / ECOS | All - Communications Working Group | [21 empty] | The Initiative’s partners agreed to keep the current hosting arrangement (EEC via the JEU), and to reconsider future hosting arrangements a a later time (Year 2) | bar: 2021 1 to 2025 4
| 1.2.6 & 1.2.7 Quarterly newsletters and Social media campaigns and assets | USAID / ECOS | All - Communications Working Group | [21 empty] | The newsletters will promote the work of the Initiative, but also aim to raise awareness of packaging issues, solutions and actions by the Initiative’s partners and other stakeholders. Creating social media content to be disseminated by the Initiative’s partners, mainly through Twitter, LinkedIn and Facebook. | bar: 2021 1 to 2025 4
Indicator | TECHNICAL STAKEHOLDER ENGAGEMENT, COORDINATION & MONITORING: OUTPUT 1.3 - Joint Initiative partners lead and actively participate in technical multi-stakeholder engagement | bar: 2021 1 to 2025 4
| 1.3.1 Technical coordination and information dissemination platform set up and used to share technical information | GLC / USAID | All | [21 empty] | Set up in Q2 2021; use throughout and beyond the Joint Initiative. GLC can provide this platform, pending funding to update it (via WREC or another funding stream) | bar: 2021 2; 2022 1 to 2022 4; 2024 1 to 2024 4
| 1.3.2 Steering Committee meets every 4 months | USAID / ECOS | All | [20 empty] | X | First meeting in April 2021. Meetings will follow TWG meetings. | bar: 2021 2; 2021 4 to 2022 4; 2023 2 to 2023 3; 2024 1 to 2025 1; 2025 3 to 2025 4
| 1.3.3 Technical working group meets every 2 months | USAID / ECOS | All | [20 empty] | X | First meeting in April 2021. Also informal virtual coffee meetings can be planned. | bar: 2021 2 to 2025 4
| 1.3.4 Project monitoring and evaluation (formal and informal) | USAID / ECOS | All | [21 empty] | Annually in Q2 & Q4. Link to policy/advocacy and standard setting & data and evidence. Bi-annual “pause and reflect” sessions as well as mid and end term evaluations. | bar: 2021 4 to 2022 4; 2023 2; 2023 4 to 2024 4; 2025 2; 2025 4
Indicator | PACKAGING DATA & EVIDENCE: OUTPUT 2.1 - Increased evidence base of current humanitarian packaging (scale of use and environmental impact) to inform the full lifecycle | [22 empty] | X | bar: 2021 1 to 2025 4
| 2.1.1. Sector wide environmental impact and scale analysis of main humanitarian packaging items/materials | WFP | USAID, WFP, UNHCR, CRS, ICRC, IOM | [21 empty] | Lead TBC - important to start in 2021 as results will be important for other outputs/activities. Will look at food and non-food to understand their scale of use and impact on the environment (from production to end of life. Includes an analysis of what KPIs we need to be able to measure our reduced environmental impact and track progress. | bar: 2021 2 to 2022 4; 2024 1 to 2024 4
| 2.1.2 LCAs of highest volume packaging items / most commonly delivered items per country/region | WFP / USAID / ECHO | IOM, GSC, CRS, UNHCR, UNHRD, UNEP LCA | [21 empty] | In 2021: Food packaging LCAs by WFP. In 2022: Additional non-food LCAs can be funded by USAID working through technical counterparts. After 2022: Possible ECHO funding through Policy Support Budget / EU's R&D budget. | bar: 2021 2 to 2024 4
| 2.1.3 Compilation of learning and best practices on humanitarian packaging waste management | USAID/ECOS | UNHCR, CRS, WFP | [21 empty] | Learning from both best practice and challenges to inform environmental/supply chain policies of humanitarian organizations and donors and be used for advocacy | bar: 2022 1 to 2022 4; 2024 1 to 2024 4
Indicator | PROCUREMENT: OUTPUT 2.2 - Improve, standardise and harmonise global procurement specifications through providing suppliers and humanitarian procurement staff with guidance/tools and integration of sustainability criteria in the tender process | bar: 2021 1 to 2025 4
| 2.2.1 Specification improvements for packaging of main relief items and standard specifications are proposed. | ? | CRS, USAID, FCDO, GLC, UNHCR, UNEP, WFP, ICRC, IOM, QSE, GSC | [21 empty] | Many partners have or are introducing specification improvements that can be shared across the sector. This would be followed by the discussion on standard specifications and how to take this forward. Data & evidence from 2.1 would feed into this. | bar: 2022 1 to 2022 4; 2024 1 to 2024 4
| 2.2.2 Set up procurement collaboration/coordination and information sharing mechanism | USAID/ECOS + ? | WFP, USAID, SAVE, FCDO, CRS, UNEP, DRC | [21 empty] | To coordinate and share data & methodologies. An informal network can start in 2021, and the mechanism can be formalised in 2022. The informal network can be started up by USAID/ECOS, and the formal network taken over and led by another partner (TBD) | bar: 2021 2 to 2022 4; 2024 1 to 2024 4
| 2.2.3 Packaging sustainability criteria list for tender contracts | DRC | ICRC, UNHCR, WFP, SAVE, USAID | [21 empty] | Various partners are already working on this and can share sustainability criteria and experience. Can be facilitated through the procurement collaboration mechanism (2.2.2) | bar: 2021 2 to 2022 4; 2024 1 to 2024 4
| 2.2.4 Concise guidance note on best packaging practices for environmentally sustainable procurement (for procurement officers) | IOM + ? (co-lead needed) | WFP, USAID, CRS, ICRC | [21 empty] | Including checklists, key recommendations, template clauses and template specs to be able to copy-paste. Could start with best practice from private sector. Various partners working on best procurement practices and can share info/finings. Builds on 2.2.1 and 2.2.3 | bar: 2021 2 to 2022 4; 2024 1 to 2024 4
| 2.2.5 Case studies of procurement best practice & learning to share with suppliers | USAID/ECOS | ICRC, WFP, ECHO, SAVE, FCDO, CRS, GLC | [21 empty] | Info can start to be gathered at the end of 2021 and case studies compiled and written up in 2022. Not only examples of best practice, but all current procurement practices for comparison and joint improvement (including "process" case studies) | bar: 2021 4 to 2022 4; 2024 1 to 2024 4
| 2.2.6 Compile all the above into one compendium: Building Circularity into Humanitarian Response through Sustainable Procurement | ? | USAID, ECHO | [21 empty] | ECHO funding can be explored. Could be part 1 of a series that could later include other supply chain & logs topics. | bar: 2022 1 to 2024 4
DESIGN, PRODUCTION & DISTRIBUTION: OUTPUT 2.3 Design, production and distribution of packaging that minimises plastic and reduces the overall environmental impact of the packaging | bar: 2021 1 to 2025 4
| 2.3.1 Database/catalogue of sustainable packaging technologies and options | Academic/ research institute + private sector partner? ECHO? | FCDO, ICRC, RISE, WFP, UNHCR, MIT, UNHRD, ECHO, USAID | [21 empty] | Including biodegradable materials/plastic alternatives; including distribution options. Could apply for ECHO Policy Support Budget funding through an implementing partner. Could start by asking large corporations to develop a catalogue from which our suppliers and partners can choose | bar: 2021 3 to 2022 4; 2024 1 to 2024 4
| 2.3.2 R&D to reevaluate the design of X common packaging products to increase sustainability (including pilots) | ICRC/WFP/UNHCR + UNHRD? | ECHO, MIT LL, Academic Partners, producers & recyclers | [21 empty] | Number and type of products will dependent on stakeholder priority & interest, ideally covering food, non-food and kits. 2021: Could focus on 1) PP bags via Innovation Norway funding (ICRC, WFP, UNHCR) and 2) UNHRD re-designed items (e..g hygiene kit). From late 2021/2022 could leverage EU's R&D funding, and could focus on specific priorities of partners (e.g those identified by UNHCR) | bar: 2021 1 to 2024 4
| 2.3.3 Innovation accelerator | ? | USAID, WFP, UNHRD | [21 empty] | For identifying and amplifying new/alternative approaches to packaging design/production | bar: 2022 1 to 2023 2; 2024 1 to 2024 4
| 2.3.4 Case studies of successes and promising packaging options and alternatives | USAID + Academic Partner | ? | [21 empty] | Feed into 2.3.1. Academic partnership to be identified. | bar: 2022 1 to 2022 4; 2024 1 to 2024 4
| 2.3.5 Baseline of packaging used in transportation and checklist of distribution improvements | USAID / ECOS | Private Sector , MIT LL | [21 empty] | To understand exactly what companies/ organizations are already doing to reduce the plastic in their shipping, and then assess what can be applied to the humanitarian sector. Private sector (e.g, commercial shipping, manufacturers); Amazon, Walmart, Kuehne Nagel, and other smaller companies could inform what we know, and then have the humanitarian assistance shipping align better with the private sector. | bar: 2022 1 to 2022 4; 2024 1 to 2024 4
END OF LIFE MANAGEMENT : OUTPUT 2.4 - Strengthened locally tailored sustainable end of life waste management in humanitarian operations through better access to tools and data | bar: 2021 1 to 2025 4
| 2.4.1 Mapping of available recycling/waste management infrastructure in operating countries | WFP + Various - based on country selection | FCDO, GLC, ICRC, CRS, WFP, UNHCR, USAID, UNEP, DRC | [21 empty] | Various orgs have offered in kind support as this aligns with their existing priorities - leads will need to be identified for specific countries based on priorities. A first step could be sharing tools, processes and data already being used to map this type of info. USAID/FCDO alignment of Caribbean region as a priority area. Results can be integrated into the GLC Logs Capacity Assessments. | bar: 2021 2 to 2022 4; 2024 1 to 2024 4
| 2.4.2 Packaging management assessment tool | JEU / USAID | UNHCR | [21 empty] | End of life waste management could integrated into NEAT+ (urban and rural). Design of a waste management module of the NEAT+ by the end of 2021. | bar: 2021 2 to 2022 4; 2024 1 to 2024 4
| 2.4.3 Packaging End of Life Management technology developed and piloted | USAID / MIT LL | WFP, ICRC, UNHCR, CRS | [21 empty] | Existing partnership between USAID and MIT LL to develop a mobile solar-powered recycling unit in 2021and pilot in 2022. Need partners in order to pilot and discussions ahead of time to make the prototype as appropriate as possible. | bar: 2021 2 to 2022 4; 2024 1 to 2024 4
| 2.4.4 Guidance on market-based opportunities for secondary use of packaging (Reuse, recycling and repurposing in X locations) | WFP | UNHCR, CRS, WFP, USAID, IFRC SRU | [21 empty] | Leads tbc based on locations & partners' priorities. Work with private sector and local actors. Design a methodology that can then be applied in other locations. Pilot solutions. Could include a fact sheet on waste types and market based solutions for types waste (global solutions). | bar: 2022 1 to 2022 4; 2024 1 to 2024 4
| 2.4.5 Catalogue of packaging management tools and methods for field use | ? | GSC ECOP | [21 empty] | To engage the field and match field needs to technological options and allow field practitioners to more easily incorporate into response. | bar: 2022 1 to 2024 4
Note on L45: Move to 2021 if WFP leading -Amanda George