## 1A_Workplan Tool
Tool 1A: Illustrative workplan for urban context Analysis
Note: This tool is a suggested starting point and should be adapted for each context.
Estimated time allocation (days)
|  | Team lead | Co-lead
Activities and sub-tasks |  | 29 | 18 | Pre-arrival | Wk1 | Wk 2 | Wk 3 | [5 empty] | Wk 4 | [5 empty] | Wk 5 | [5 empty] | Wk 6
[8 empty] | M | T | W | Th | F |  | M | T | W | Th | F |  | M | T | W | Th | F
Phase 1 Preparation (Steps 1-3)
| Internal work planning, framing of analysis and prioritising of geographic areas, questions | 2
Phase 2: Data collection (Steps 4-6)
| Conduct desk review | 4
| Preliminary data collection planning | 1
| City overview workshop (one day for participants) | 1 | 1
| Identify first-tier key informants and detailed field planning | 2 | 2
| Adapt/revise tools and update draft sampling plan for KIIs and FGDs | 1 | 1
| Prepare for and organise KIIs/FGDs (includes training of interviewers - follow-ups, protection considerations, etc.) | 1.5 | 1
| Implementation of FGDs | 2.5 | 2.5
| Implementation of sub-area level and city-wide KIIs | 4.5 | 4.5
Phase 3: Data analysis and documenting (Steps 7-10)
| Data analysis | 1 | 2.5
| Validation Workshop with staff/partners | 1 | 1
| Report writing | 3.5 | 2.5
| Revisions to report following feedback from internal stakeholders/Debriefing with country programme/sector leads | 2.5
| Presentation of summary results to external stakeholders | 1.5
| Submit final report (end of week 6) | n/a
Optional activities are presented in italics

## 1B_Budget Tool
Tool 1B: Illustrative budget for urban context analysis
Note: This tool is a suggested starting point and should be adapted for each context.
Category | Unit rate | No of units | Sub-total
Technical support or consultant services (if any team members are consultants or require budget allocation)
Team lead |  |  | 0
Co-Lead |  |  | 0
Sub-total services |  |  | 0
Travel Expenses
Flights (Int'l) |  |  | 0
In-country transportation (flights, vehicle hire, local transport etc.) |  |  | 0
Visa(s) |  |  | 0
Lodging |  |  | 0
Per diem |  |  | 0
Sub-total travel |  |  | 0
Activities
Translators (daily rate, per diem, etc.) |  |  | 0
Workshop expenses (rental, meals, transport fees, etc.) |  |  | 0
Meeting space (if necessary for FGDs, etc., but only if no community options are possible) |  |  | 0
Phones/phone credit |  |  | 0
Printing data collection materials |  |  | 0
Sub-total activities |  |  | 0
GRAND TOTAL |  |  | 0